## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 10.05.2023 - 14:30
Team Number |  | 3
Participant 1 |  | Maria Mirnic
Participant 2 |  | Nazia Nazari
Participant 3 |  | Safwan Zullash
Mentor |  | Lukas Rohatsch
List the IDs of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
0 | Created Repo + Organisation Structure | 1 | 1 | 0 | 1
0d | Organised File Structure | 1 | 1 | 0 | 1
0e | Central DB-Class and Access | 1 | 1 | 0 | 1 |  | xampp issues
1a | User can register | 4 | 6 | 2 | 1 |  | xampp issues
1e | Password hashed in DB | 0.5 | 0.5 | 0 | 1
1f | Admin-User set in DB | 0.25 | 0.25 | 0 | 1
2a | Login Form | 1 | 1 | 0 | 1
2c | Login works | 2 | 6 | 4 | 1
2d | Logout works | 1 | 6 | 5 | 1 |  | xampp issues
2e | Different Navbar depending on User | 1 | 4 | 3 | 1 |  | xampp issues
2g | Remember Me works | 1 | 4 | 3 | 1 |  | xampp issues
3a | Products List and Categories | 2 | 6 | 4 | 1
3b | Products can be added to cart w/o page reload | 1 | 2 | 1 | 1
3c | Cart Count visible | 0.5 | 0.25 | -0.25 | 1
3g | Products can be removed from cart | 1 |  | -1 |  | 1
4a | Search w/ continuous filter | 1 |  | -1 |  | 1
1 |  |  |  | 19.75 | 14 | 2